## Changes On 03Nov2015
Page | Changes
Home Page Master Page and Website | Check Responsiveness of Website | Maheshbhai
Review Menu Icons and suggest new icons if required
Make Header smaller and Iconsize accordingly for HomePage and Master Page Icons
Header of Portal should be Static on Top of website.
30 day free trial should be hilighted on home page.
Suggest New Banner Images and Shuffle with existing one. (Note Ashokbhai has some ideas about the same.)
Sample Videos | Create 10 to 15 Videos of 1 to 1:30 minutes length for Youtube channel and google analytics from our existing content. Take Help from Jay to create the sample videos | Ripal
| Share and Redirect Link/Icons for Facebook, Tweeter, Google + etc. | Dhaval
Minimize Server Round Trip
Login | Use Popup for Login process instead of a separate Login page.
Dashboard | Col. 1 for Subject List
Col. 2 for Selection of Chapter and Topic (Covered / Uncovere Topics should be displayed in different colours
Graphical Respresantation is required for covered and uncovered chahpter i.e. Circular Chart
Educational Resources and Animation should remain on the dashboard page only to reduce server round trip.
Packages | There should be separate page for Packages and related information. Dashboard should contain small popup or link for packages and related information.
Package Plan needs to decided.
Add Cource info and available packages page.
Reports
Analytical reports should be there on Portal for Parents and sent through email weely to parents
Time recording of chapter topic and its usage by student report should be there.
Registration Flow Chart | Registration form should ask for minimum fields to fill for user like. Name, Email, Contact No.
After filling up the form Credential should be sent to registered user through email.
On Logging into the website, portal should ask to fill the full profile of a student/user.
There Should be two Tabs for Profile detail seperation.
1. Personal Info
2. Educational Information
Personal Info tab should contain Details of Student, Parent and their email and communication/mobile no.
Educational Information tab should contail user/student's School Name and its information and his/her current Board, Medium, Standard in different dropdown boxes.
Nilofar | Create a Control for Login / Forgot Password / Registration
Crate Individual Pages for Package from which All packages information can be retrive
Pavan | Develop Profile and navigation flow of profile, menu, Header etc.
Dhaval | Dashboard design, FaceBook, Tweeter, Google+ Links
Ripal | Sample Videos and Testing
Maheshbhai | Homepage Design and make website responsive
Reports | Dishaben
Ripal | Set Header script to all pages,
Put Tweeter, Facebook , Google+ Script to all pages

## New Changes
Priority Task
1 | Put Register/Signup Menu (Rename it to Signup) on each Pre Logged in Form (Note: Signup Menu should not appear on Post Login Pages) | Pavan
2 | Landing Page: Change Headings of the Description as per the Word Document Sent by Ashokbhai | Pavan
3 | Replace E-Pathshala, e-Pathshala, Epathshala etc. words with Common word ePathshala (where e Should be in small letter and P letter in capital) Whole Website. | Ripal
4 | Menu should remain closed while loading the Page (Whole website) | Pavan
5 | Upload MP4 files instead of SWF Files as content on web. | Ripal Soni
6 | Add type attribute under script tag. | Ripal Soni
Pending for Approval / Discussion
1 | Current Package, Expired Packages, Buy Package etc. under Account Information | Nilofar
2 | Changes in User Profile, We may consider selfie.net.in as referance
3 | Redesign Dashboard as per new requirement. Requirements will be suggested by Ashokbhai
4 | Changes in Package and Prices will be provided by Ashokbhai | Nilofar

## Completed Tasks
Epathshala Student Portal
Pages | Path | Assigned To | Status | Do it by tomorrow day end | Remark-1 | Remark-2 | Remark-3
Landing Page | Landing.htm | Ripal Soni | Done | Verified | Register Now Link is not working on Slide Show. For Both Landing page and login page. | Required Url On Demo Videos - Ripal | Epathshala - Transforming Learning Through Technology Header - bellow paragraph Text Required Justify
Change Password | MasterPage\Epathshala.Master | Pavan Upadhyay | Done | Need to verify | Need to clear text box of new password and change password on load. - Same on Search text box of Dashboard. - Pavan
Contact Us | SitePages\Contact_Us.aspx | Pavan Upadhyay | Done | Need to verify
Login Page | OtherPages\Login.aspx | Varnindra Panchal | Done | Verified | Slide Show required to set size of Images + Panel | slideshow not properly view in mobile view | login page slide show required to create link fro registration
Dashboard | Dashboard\StudentDashboard.aspx | Varnindra Panchal | Done | Verified
Student Profile Pages (2) | [1] Student\StudentProfile.aspx [2]UserManagement/UpdateProfileStudent.aspx | Dhaval Patel | Done | Need to verify
Buy Package | DashBoard/BuyPackage.aspx | Nilofar Dabhi | Pending | Need to verify
Student Report | Report/StudentPackageReport.aspx | Nilofar Dabhi | Pending | Start tomorrow after tea time | Require page more simple & Clear
Add profile pic in header master page |  | Pavan Upadhyay | Done | Need to varify
Subject wise exam result | Report/SubjectWiseReportF.aspx | Disha Vaghela | Done | Need to Varify | Required to all Droup down menu must be in same size
Education Resource | Dashboard/EducationalResource.aspx?Type=Student | Pavan Upadhyay | Done | Need to varify | Require highlite to play option for animation link or in text
Student Assessment | Student\StudentAssessment.aspx | Pavan with VP | Working | Tomorrow morning for VP if possible
Change Menubar with Icons | All Pages with Containing Menubar/Header | Pavan Upadhyay | Done
Master Pages(3) | [1] MasterPage\Epathshala.Master [2] MasterPage\CommonHeaderFooter.Master [3] MasterPage\LoginMasterPage.Master | Pavan Upadhyay | Done | Need to verify
Payment Pages (3 Pages) | [1] Dashboard\ BuyPackage.aspx [2] Dashboard\PackageConfirmation.aspx [3] Dashboard\PackagePaymentNew.aspx | Nilofar Dabhi | Done | Need to verify
About Us | OtherPages\AboutUs.aspx | Ripal Soni | Done | Need to verify | About Us Bellow paregraph required to Justify
Contact | OtherPages\ContactUs.aspx | Ripal Soni | Done | Need to verify
Registration Page | OtherPages\Registration.aspx | Ripal Soni | Done | Need to verify | Male /Female Radio buttion Put Space After That
Footer Link Pages (FAQs,Policy Etc) Inside Panel (4 Pages) | All .aspx Pages under > Policy Folder WITHOUT 'Login' Prefix | Ripal Soni | Done | Need to Verified
Footer Link Pages (FAQs,Policy Etc) Outside the Panel (4 Pages) | All .aspx Pages under > Policy Folder WITH 'Login' Prefix | Nilofar Dabhi | Done | Verified
Dashboard cover syllabus click result of pretest posttest | Dashboard\StudentDashboard.aspx | Dhaval Patel | Pending | Start on 30th oct morning | Search Panel not clear
Add Google Analytics Track in all Pages of Epatshala | In All Applicable pages of Epathshala | Ripal Soni | Done | 29th Oct,2015
Total Pages : 29 Pages
| Remove Other Ventures from Master Page after login | Varnindra
| Calender Image colour should be same - Entire Solution | Dhaval
| Put Circular Chart on Result Page | Dhaval

## Dashboard
Dashboard
You are here: Dashboard |  |  |  | Today: 20 May 15 |  | Search
Subjects |  | Chapter Topic |  |  | Educational Resources
Maths |  | Chapter 1 |  |  | Pre Test
Science |  | Topic - 1 |  |  | 01 Video Presentation
Social Science |  | Topic - 2 | Topic - 2 |  | MCQ Level-1
English |  | Chapter 2 |  |  | MCQ Level-2
Hindi |  | Topic - 1 | Topic - 1 |  | MCQ Level-3
|  | Topic - 2 | Topic - 2 |  | Worksheet Level-1
|  | Chapter 3 |  |  | Worksheet Level-2
|  | Topic - 1 |  |  | Worksheet Level-3
|  | Topic - 2 |  |  | Post Test
| Selected |  | Covered Chapter
Uncovered Chapter
Covered Syllabus Chart
Popup - Animation / Worksheet / MCQ / Pre Test & Post Test

## Login
Login |  |  | Register User
| Login ID |  |  | First Name *
| Passowrd |  |  | Last Name
| OK | Cancel |  | Contact No
| Forgot Password? |  |  | Email ID *
New User? Register
School
Forgot Password |  |  |  | Board
| Login ID |  |  | Medium
| OK | Cancel |  | Standard
Password has been sent to your email |  |  |  | OK |  | Cancel
Dropdown list